## Diagram
|  |  | ES = max(EF of predecessors) |  | Activity ID |  | EF = ES+D
|  |  | TS = LS - ES |  | Activity Description |  | FS = ES of Earliest Succcessor - EF
|  |  | LS = LF - D |  | D = Activity Duration |  | LF = min(LS of successors)
|  |  |  | 5 | A | 10 |  | 10 | F | 15 |  | 15 | I | 50 |  | 50 | K | 56 | 144 | O | 150 |  | 150 | R | 174
|  |  |  | 88 | Create Data Tables | 0 | 2 | 88 | Compile List of Websites | 0 | 2 | 88 | Write Scraping Code | 0 | 2 | 88 | Automate | 88 | 0 | Connect DB to App | 0 | 2 | 0 | Test Security | 0
|  |  |  | 93 | 5 | 98 |  | 98 | 5 | 103 |  | 103 | 35 | 138 |  | 138 | 6 | 144 | 144 | 6 | 150 |  | 150 | 24 | 174
|  |  |  | 5 | B | 8 |  | 8 | G | 22 |  | 22 | J | 36 |  | 36 | L | 39 | 144 | P | 150 |  | 150 | S | 162
|  |  |  | 117 | Convert Algorithm to Python | 0 | 2 | 117 | Backtest Model | 0 | 2 | 117 | Validate Pyton Model | 0 | 2 | 117 | Export Model | 105 | 12 | Import model into App | 0 | 2 | 12 | Test Predictions | 12
|  |  |  | 122 | 3 | 125 |  | 125 | 14 | 139 |  | 139 | 14 | 153 |  | 153 | 3 | 156 | 156 | 6 | 162 |  | 162 | 12 | 174
0 | AA | 5 |  | 5 | C | 20 |  | 20 | H | 44 | [5 empty] | 44 | M | 144 | 144 | Q | 156
0 | Project Charter | 0 | 2 | 0 | Wire Frame App | 0 | 2 | 0 | Design Pages | 0 | [5 empty] | 0 | Code App | 0 | 18 | Test App | 18
0 | 5 | 5 |  | 5 | 15 | 20 |  | 20 | 24 | 44 | [5 empty] | 44 | 100 | 144 | 162 | 12 | 174
|  |  |  | 5 | D | 35 | [19 empty] | 174 | T | 184 |  | 184 | U | 185
|  |  |  | 139 | Create Marketing Plan | 139 | [19 empty] | 0 | Launch Campaign | 0 | 2 | 0 | App Goes Live | 0
|  |  |  | 144 | 30 | 174 | [19 empty] | 174 | 10 | 184 |  | 184 | 1 | 185
6
|  |  |  | 5 | E | 14 | [9 empty] | 14 | N | 20 | [11 empty] | 185 | V | 188 |  | 188 | W | 203 |  | 203 | X | 209
|  |  |  | 165 | Define KPIs | 0 | [9 empty] | 165 | Validate Ability to Track KPIs | 165 | [11 empty] | 0 | Track KPIs | 0 | 2 | 0 | Build Reports | 0 | 2 | 0 | Evaluate Results | 0
|  |  |  | 170 | 9 | 179 | [9 empty] | 179 | 6 | 185 | [11 empty] | 185 | 3 | 188 |  | 188 | 15 | 203 |  | 203 | 6 | 209

## Network Information Table
Network Information Table
Activity ID | Activity Description | Preceding Activity | Activity Duration | Free Slack | Total Slack
AA | Project Charter | None | 5 | 0 | 0
A | Create Data Tables | AA | 5 | 0 | 88
B | Convert Algorithm to Python | AA | 3 | 0 | 117
C | Wire Frame App | AA | 15 | 0 | 0
D | Create Marketing Plan | AA | 30 | 139 | 139
E | Define KPIs | AA | 9 | 0 | 165
F | Compile List of Websites | A | 5 | 0 | 88
G | Backtest Model | B | 14 | 0 | 117
H | Design Pages | C | 24 | 0 | 0
I | Write Scraping Code | F | 35 | 0 | 88
J | Validate Pyton Model | G | 14 | 0 | 117
K | Automate Data Pipeline | I | 6 | 88 | 88
L | Export Model | J | 3 | 105 | 117
M | Code App | H | 100 | 0 | 0
N | Validate Ability to Track KPIs | E | 6 | 165 | 165
O | Connect DB to App | K, M | 6 | 0 | 0
P | Import model into App | L, M | 6 | 0 | 12
Q | Test App | M | 12 | 18 | 18
R | Test Security | O | 24 | 0 | 0
S | Test Predictions | P | 12 | 12 | 12
T | Launch Campaign | D, Q, R, S | 10 | 0 | 0
U | App Goes Live | T | 1 | 0 | 0
V | Track KPIs | N, U | 3 | 0 | 0
W | Build Reports | W | 15 | 0 | 0
X | Evaluate Results | X | 6 | 0 | 0
|  | Total Duration | 369
|  | Critical Path Duration | 209