## EVA
ACTIVITY ID | DURATION | TASK NAME | BUDGET (PV) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42
AA | 5 | Project Charter | 1000 | Week 1: 1000
A | 5 | Create Data Tables | 4000 | Week 2: 4000
B | 3 | Convert Algorithm to Python | 5000 | Week 2: 5000
C | 15 | Wire Frame App | 7000 | Week 2: 2333; Week 3: 2333; Week 4: 2334; Week 5: x
D | 30 | Create Marketing Plan | 11250 | Week 2: 1875; Week 3: 1875; Week 4: 1875; Week 5: 1875; Week 6: 1875; Week 7: 1875
E | 9 | Define KPIs | 4000 | Week 2: 2000; Week 3: 2000
F | 5 | Compile List of Websites | 4500 | Week 3: 4500
G | 14 | Backtest Model | 13500 | Week 3: 4500; Week 4: 4500; Week 5: 4500; Week 6: x; Week 7: x
H | 24 | Design Pages | 13500 | Week 5: x; Week 6: 2700; Week 7: 2700; Week 8: 2700; Week 9: 2700; Week 10: 2700; Week 11: 2700
I | 35 | Write Scraping Code | 35500 | Week 4: 5071.4286; Week 5: 5071.4286; Week 6: 5071.4286; Week 7: 5071.4286; Week 8: 5071.4286; Week 9: 5071.4286; Week 10: 5071.4286
J | 14 | Validate Pyton Model | 13500 | Week 5: 4500; Week 6: 4500; Week 7: 4500
K | 6 | Automate Data Pipeline | 5500 | Week 11: 5500
L | 3 | Export Model | 2500 | Week 8: 2500
M | 100 | Code App | 66000 | Week 10: 3300; Week 11: 3300; Week 12: 3300; Week 13: 3300; Week 14: 3300; Week 15: 3300; Week 16: 3300; Week 17: 3300; Week 18: 3300; Week 19: 3300; Week 20: 3300; Week 21: 3300; Week 22: 3300; Week 23: 3300; Week 24: 3300; Week 25: 3300; Week 26: 3300; Week 27: 3300; Week 28: 3300; Week 29: 3300
N | 6 | Validate Ability to Track KPIs | 2750 | Week 30: 2750
O | 6 | Connect DB to App | 2750 | Week 30: 2750
P | 6 | Import model into App | 3500 | Week 30: 3500
Q | 12 | Test App | 6750 | Week 30: 2250; Week 31: 2250; Week 32: 2250
R | 24 | Test Security | 13250 | Week 31: 2650; Week 32: 2650; Week 33: 2650; Week 34: 2650; Week 35: 2650
S | 12 | Test Predictions | 9000 | Week 31: 3000; Week 32: 3000; Week 33: 3000
T | 10 | Launch Campaign | 5750 | Week 36: 2875; Week 37: 2875
U | 1 | App Goes Live | 1000 | Week 38: 1000
V | 3 | Track KPIs | 1500 | Week 38: 1500
W | 15 | Build Reports | 16000 | Week 39: 5333.3333; Week 40: 5333.3333; Week 41: 5333.3333
X | 6 | Evaluate Results | 5000 | Week 42: 5000
Week Total |  |  | 254000 | 1000 | 15208 | 15208 | 13780.4286 | 15946.4286 | 14146.4286 | 14146.4286 | 10271.4286 | 7771.4286 | 11071.4286 | 11500 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 11250 | 7900 | 7900 | 5650 | 2650 | 2650 | 2875 | 2875 | 2500 | 5333.3333 | 5333.3333 | 5333.3333 | 5000
Cummulative PV |  |  |  | 1000 | 16208 | 31416 | 45196.4286 | 61142.8571 | 75289.2857 | 89435.7143 | 99707.1429 | 107478.5714 | 118550 | 130050 | 133350 | 136650 | 139950 | 143250 | 146550 | 149850 | 153150 | 156450 | 159750 | 163050 | 166350 | 169650 | 172950 | 176250 | 179550 | 182850 | 186150 | 189450 | 200700 | 208600 | 216500 | 222150 | 224800 | 227450 | 230325 | 233200 | 235700 | 241033.3333 | 246366.6667 | 251700 | 256700
End of Period 1
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | 0% | 0 | 0 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: EV = Comp% x PV
B | 0% | 0 | 0 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: CV = EV - AC
C | 0% | 0 | 0 | Week 1: 7000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: SV = EV - PV
D | 0% | 0 | 0 | Week 1: 11250; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: CPI = EV / AC
E | 0% | 0 | 0 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: SPI = EV / PV
F | 0% | 0 | 0 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
G | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 2
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 7: By end of period 2 we are alreadya little behind schedule on task C (Wire Frame App) this is along the critical path
C | 33% | 2310 | 2500 | Week 1: 7000; Week 2: -190; Week 3: -4690; Week 4: 0.924; Week 5: 1
D | 16% | 1800 | 1800 | Week 1: 11250; Week 2: 0; Week 3: -9450; Week 4: 1; Week 5: 1
E | 50% | 2000 | 2000 | Week 1: 4000; Week 2: 0; Week 3: -2000; Week 4: 1; Week 5: 1; Week 8: 4666; Week 9: 9332
F | 0% | 0 | 0 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 8: work remaining
G | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 8: CPI
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 7000
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 2310
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 2500
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 3
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | 50% | 3500 | 4666 | Week 1: 7000; Week 2: -1166; Week 3: -3500; Week 4: 0.75011; Week 5: 0.5
D | 33% | 3712.5 | 3750 | Week 1: 11250; Week 2: -37.5; Week 3: -7537.5; Week 4: 0.99; Week 5: 0.33; Week 7: Task C is behind pace
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 8: 2333.3333; Week 9: 9333.3333
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 33% | 4455 | 4500 | Week 1: 13500; Week 2: -45; Week 3: -9045; Week 4: 0.99; Week 5: 0.33
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 4
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | 75% | 5250 | 7000 | Week 1: 7000; Week 2: -1750; Week 3: -1750; Week 4: 0.75; Week 5: 0.75; Week 7: We can't start task H until C is complete… But that was delayed so now this project start is pushed back a week
D | 50% | 5625 | 5625 | Week 1: 11250; Week 2: 0; Week 3: -5625; Week 4: 1; Week 5: 0.5; Week 7: Task G is more difficult than anticipated and is running behind pace
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 40% | 5400 | 9000 | Week 1: 13500; Week 2: -3600; Week 3: -8100; Week 4: 0.6; Week 5: 0.4; Week 7: 22500
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 15% | 5325 | 5071 | Week 1: 35500; Week 2: 254; Week 3: -30175; Week 4: 1.0501; Week 5: 0.15
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 5
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | Finished | 7000 | 9333 | Week 1: 7000; Week 2: -2333; Week 3: 0; Week 4: 0.75003; Week 5: 1
D | 66% | 7425 | 7500 | Week 1: 11250; Week 2: -75; Week 3: -3825; Week 4: 0.99; Week 5: 0.66; Week 7: Task G is behind pace. It's not along the critical path and will not cause delays to the overall project
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 7: We had a little jump start on Task H to try and make up some ground we lost.
G | 60% | 8100 | 13500 | Week 1: 13500; Week 2: -5400; Week 3: -5400; Week 4: 0.6; Week 5: 0.6; Week 7: 22500
H | 10% | 1350 | 1000 | Week 1: 13500; Week 2: 350; Week 3: -12150; Week 4: 1.35; Week 5: 0.1
I | 30% | 10650 | 10143 | Week 1: 35500; Week 2: 507; Week 3: -24850; Week 4: 1.05; Week 5: 0.3
J | 33% | 4455 | 4500 | Week 1: 13500; Week 2: -45; Week 3: -9045; Week 4: 0.99; Week 5: 0.33
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 6
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | Finished | 7000 | 9333 | Week 1: 7000; Week 2: -2333; Week 3: 0; Week 4: 0.75003; Week 5: 1
D | 84% | 9450 | 9375 | Week 1: 11250; Week 2: 75; Week 3: -1800; Week 4: 1.008; Week 5: 0.84; Week 7: Task G is killing us
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 80% | 10800 | 18000 | Week 1: 13500; Week 2: -7200; Week 3: -2700; Week 4: 0.6; Week 5: 0.8
H | 30% | 4050 | 3700 | Week 1: 13500; Week 2: 350; Week 3: -9450; Week 4: 1.0946; Week 5: 0.3
I | 43% | 15265 | 15214 | Week 1: 35500; Week 2: 51; Week 3: -20235; Week 4: 1.0034; Week 5: 0.43
J | 66% | 8910 | 9000 | Week 1: 13500; Week 2: -90; Week 3: -4590; Week 4: 0.99; Week 5: 0.66
K | 0% | 0 | 0 | Week 1: 5500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 2500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 66000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0

## EVA 6 Periods
End of Period 1
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
Cumulative Totals |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | 1
End of Period 2
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 33% | 2310 | 2500 | 2310 | -190 | 0 | 0.924 | 1
D | 16% | 1800 | 1800 | 1800 | 0 | 0 | 1 | 1
E | 50% | 2000 | 2000 | 2000 | 0 | 0 | 1 | 1
Cumulative Totals |  | 16110 | 16300 | 16110 | -190 | 0 | 0.98834 | 1
End of Period 3
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 50% | 3500 | 4666 | 4690 | -1166 | -1190 | 0.75011 | 0.74627
D | 33% | 3712.5 | 3750 | 3712.5 | -37.5 | 0 | 0.99 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 33% | 4455 | 4500 | 4455 | -45 | 0 | 0.99 | 1
Cumulative Totals |  | 30167.5 | 31416 | 31357.5 | -1248.5 | -1190 | 0.96026 | 0.96205
End of Period 4
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 75% | 5250 | 7000 | 7000 | -1750 | -1750 | 0.75 | 0.75
D | 50% | 5625 | 5625 | 5625 | 0 | 0 | 1 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 40% | 5400 | 9000 | 9045 | -3600 | -3645 | 0.6 | 0.59701
H | 0% | 0 | 0 | 2700 | 0 | 0 | 0 | 0
I | 15% | 5325 | 5071 | 5071.4286 | 254 | 253.5714 | 1.0501 | 1.05
Cumulative Totals |  | 40100 | 45196 | 47941.4286 | -5096 | -5141.4286 | 0.88725 | 0.83644
End of Period 5
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | Finished | 7000 | 9333 | 7000 | -2333 | 0 | 0.75003 | 1
D | 66% | 7425 | 7500 | 7425 | -75 | 0 | 0.99 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 60% | 8100 | 13500 | 13500 | -5400 | -5400 | 0.6 | 0.6
H | 10% | 1350 | 1000 | 2700 | 350 | -1350 | 1.35 | 0.5
I | 30% | 10650 | 10143 | 10142.8571 | 507 | 507.1429 | 1.05 | 1.05
J | 33% | 4455 | 4500 | 4455 | -45 | 0 | 0.99 | 1
Cumulative Totals |  | 57480 | 64476 | 63722.8571 | -6996 | -6242.8571 | 0.89149 | 0.90203
End of Period 6
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | Finished | 7000 | 9333 | 7000 | -2333 | 0 | 0.75003 | 1
D | 84% | 9450 | 9375 | 11250 | 75 | -1800 | 1.008 | 0.84
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 80% | 10800 | 18000 | 13500 | -7200 | -2700 | 0.6 | 0.8
H | 30% | 4050 | 3700 | 5400 | 350 | -1350 | 1.0946 | 0.75
I | 43% | 15265 | 15214 | 15214.2857 | 51 | 50.7143 | 1.0034 | 1.0033
J | 66% | 8910 | 9000 | 9045 | -90 | -135 | 0.99 | 0.98507
Cumulative Totals |  | 73975 | 83122 | 79909.2857 | -9147 | -5934.2857 | 0.88996 | 0.92574

## Status Report
Project Number: 2323 |  | Project Manager: Amanda Whiting
Project Priority Now: 1
Status as of: August 15, 2019
Earned Value Figures:
PV | EV | AC | SV | CV | BAC
79909 | 73975 | 83122 | -5934 | -9147 | 254000 | 285407.07
EAC | VAC | EAC t | CPI | PCIB | PCIC
263147 | -22260.07 | 285407.07 | 0.88996 | 29.12% | 31.59% | 1090640 | 1107469 | -16829
Project Description: An iPhone Application The iPhone Application Project will put A.I. Sports in a league of our own, enabling our partners, investors, and clients access to our real time predictions and recommendations for every sports investment opportunity.
Status Summary: We have completed 6 tasks. We have two additional tasks that are over 80% complete. We are running slightly behind schedule and over budget. Tasks C and G are the pain points.
Explanations: Task C fell behind schedule. The developers provided feedback that some of the requirements needed for the application are logistically problematic. We followed change protocol to decrease the total number of pages by combining two stakeholder requirements onto the same page. The revised estimate cost at completion (EAC) for task C is $9,333. This task is on the critical path and will push back the overall project timeline by two weeks.
We had anticipated a possibly that the data science team may run into a problem with their new model. However, there was substantial degradation to our new model when compared to our in-house model. This task does not lie on the critical path, but the costs will increase trying to solve the problem. The revised estimate cost at completion (EAC) for task G is now $22,500.
Major Changes Since Last Report:Our revised estimate for completing the progress is 2 weeks later than our planned project duration.
Total Cost of Approved Changes: Task C increased by $2,333. Task G increased by $9,000. This leaves us at Total Cost Increase = $11,333
Projected Cost at Completion: The forecasted total cost at completion is estimated to be $285,407.
Risk Watch: There are no signs of any increase in the risk of the upcoming tasks.

## Final Question 4
End of Day 34
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | 50% | 2000 | 2200 | 1800 | -200 | 200 | 0.90909 | 1.1111
Cumulative Totals |  | 2000 | 2200 | 1800 | -200 | 200 | 0 | 1.1111
End of Period 2
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 33% | 2310 | 2500 | 2310 | -190 | 0 | 0.924 | 1
D | 16% | 1800 | 1800 | 1800 | 0 | 0 | 1 | 1
E | 50% | 2000 | 2000 | 2000 | 0 | 0 | 1 | 1
Cumulative Totals |  | 16110 | 16300 | 16110 | -190 | 0 | 0.98834 | 1
End of Period 3
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 50% | 3500 | 4666 | 4690 | -1166 | -1190 | 0.75011 | 0.74627
D | 33% | 3712.5 | 3750 | 3712.5 | -37.5 | 0 | 0.99 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 33% | 4455 | 4500 | 4455 | -45 | 0 | 0.99 | 1
Cumulative Totals |  | 30167.5 | 31416 | 31357.5 | -1248.5 | -1190 | 0.96026 | 0.96205
End of Period 4
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | 75% | 5250 | 7000 | 7000 | -1750 | -1750 | 0.75 | 0.75
D | 50% | 5625 | 5625 | 5625 | 0 | 0 | 1 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 40% | 5400 | 9000 | 9045 | -3600 | -3645 | 0.6 | 0.59701
H | 0% | 0 | 0 | 2700 | 0 | 0 | 0 | 0
I | 15% | 5325 | 5071 | 5071.4286 | 254 | 253.5714 | 1.0501 | 1.05
Cumulative Totals |  | 40100 | 45196 | 47941.4286 | -5096 | -5141.4286 | 0.88725 | 0.83644
End of Period 5
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | Finished | 7000 | 9333 | 7000 | -2333 | 0 | 0.75003 | 1
D | 66% | 7425 | 7500 | 7425 | -75 | 0 | 0.99 | 1
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 60% | 8100 | 13500 | 13500 | -5400 | -5400 | 0.6 | 0.6
H | 10% | 1350 | 1000 | 2700 | 350 | -1350 | 1.35 | 0.5
I | 30% | 10650 | 10143 | 10142.8571 | 507 | 507.1429 | 1.05 | 1.05
J | 33% | 4455 | 4500 | 4455 | -45 | 0 | 0.99 | 1
Cumulative Totals |  | 57480 | 64476 | 63722.8571 | -6996 | -6242.8571 | 0.89149 | 0.90203
End of Period 6
Task | %Complete | EV | AC | PV | CV | SV | CPI | SPI
AA | Finished | 1000 | 1000 | 1000 | 0 | 0 | 1 | 1
A | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
B | Finished | 5000 | 5000 | 5000 | 0 | 0 | 1 | 1
C | Finished | 7000 | 9333 | 7000 | -2333 | 0 | 0.75003 | 1
D | 84% | 9450 | 9375 | 11250 | 75 | -1800 | 1.008 | 0.84
E | Finished | 4000 | 4000 | 4000 | 0 | 0 | 1 | 1
F | Finished | 4500 | 4500 | 4500 | 0 | 0 | 1 | 1
G | 80% | 10800 | 18000 | 13500 | -7200 | -2700 | 0.6 | 0.8
H | 30% | 4050 | 3700 | 5400 | 350 | -1350 | 1.0946 | 0.75
I | 43% | 15265 | 15214 | 15214.2857 | 51 | 50.7143 | 1.0034 | 1.0033
J | 66% | 8910 | 9000 | 9045 | -90 | -135 | 0.99 | 0.98507
Cumulative Totals |  | 73975 | 83122 | 79909.2857 | -9147 | -5934.2857 | 0.88996 | 0.92574

## Final Quest 4 status
Project Number: 2323 |  | Project Manager: Jason Lee
Project Priority Now: 1
Status as of: August 31, 2019
Earned Value Figures:
PV | EV | AC | SV | CV | BAC
1800 | 2000 | 2200 | 200 | -200 | 3600 | 3960
EAC | VAC | EAC t | CPI | PCIB | PCIC
3800 | -160 | 3960 | 0.90909 | 55.56% | 57.89% | 1090640 | 1107469 | -16829
Project Description: An iPhone Application The iPhone Application Project will put A.I. Sports in a league of our own, enabling our partners, investors, and clients access to our real time predictions and recommendations for every sports investment opportunity.
Status Summary: We have completed 6 tasks. We have two additional tasks that are over 80% complete. We are running slightly behind schedule and over budget. Tasks C and G are the pain points.
Explanations: Task C fell behind schedule. The developers provided feedback that some of the requirements needed for the application are logistically problematic. We followed change protocol to decrease the total number of pages by combining two stakeholder requirements onto the same page. The revised estimate cost at completion (EAC) for task C is $9,333. This task is on the critical path and will push back the overall project timeline by two weeks.
We had anticipated a possibly that the data science team may run into a problem with their new model. However, there was substantial degradation to our new model when compared to our in-house model. This task does not lie on the critical path, but the costs will increase trying to solve the problem. The revised estimate cost at completion (EAC) for task G is now $22,500.
Major Changes Since Last Report:Our revised estimate for completing the progress is 2 weeks later than our planned project duration.
Total Cost of Approved Changes: Task C increased by $2,333. Task G increased by $9,000. This leaves us at Total Cost Increase = $11,333
Projected Cost at Completion: The forecasted total cost at completion is estimated to be $285,407.
Risk Watch: There are no signs of any increase in the risk of the upcoming tasks.