## Gantt
iPhone Application Project
A.I. Sports
Jason Lee
ACTIVITY ID | TASK NAME | START DATE | DUE DATE | DURATION | ES | LS | EF | LF | TOTAL SLACK | FREE SLACK | TOTAL PV | PRIORITY | SPRINT/MILESTONE
AA | Project Charter | 2019-07-01 | 2019-07-06 | 5 | 0 | 0 | 5 | 5 | 0 | 0 |  | Critical Path | Phase 1
A | Create Data Tables | 2019-07-06 | 2019-07-11 | 5 | 5 | 93 | 10 | 98 | 88 | 0 |  |  | Phase 1
B | Convert Algorithm to Python | 2019-07-06 | 2019-07-09 | 3 | 5 | 122 | 8 | 125 | 117 | 0 |  |  | Phase 1
C | Wire Frame App | 2019-07-06 | 2019-07-21 | 15 | 5 | 5 | 20 | 20 | 0 | 0 |  | Critical Path | Phase 1
D | Create Marketing Plan | 2019-07-06 | 2019-08-05 | 30 | 5 | 144 | 35 | 174 | 139 | 139 |  |  | Phase 1
E | Define KPIs | 2019-07-06 | 2019-07-15 | 9 | 5 | 170 | 14 | 179 | 165 | 0 |  |  | Phase 1
F | Compile List of Websites | 2019-07-11 | 2019-07-16 | 5 | 10 | 98 | 15 | 103 | 88 | 0 |  |  | Phase 2
G | Backtest Model | 2019-07-09 | 2019-07-23 | 14 | 8 | 125 | 22 | 139 | 117 | 0 |  |  | Phase 2
H | Design Pages | 2019-07-21 | 2019-08-14 | 24 | 20 | 20 | 44 | 44 | 0 | 0 |  | Critical Path | Phase 2
I | Write Scraping Code | 2019-07-16 | 2019-08-20 | 35 | 15 | 103 | 50 | 138 | 88 | 0 |  |  | Phase 2
J | Validate Pyton Model | 2019-07-23 | 2019-08-06 | 14 | 22 | 139 | 36 | 153 | 117 | 0 |  |  | Phase 2
K | Automate Data Pipeline | 2019-08-20 | 2019-08-26 | 6 | 50 | 138 | 56 | 144 | 88 | 88 |  |  | Phase 2
L | Export Model | 2019-08-06 | 2019-08-09 | 3 | 36 | 153 | 39 | 156 | 117 | 105 |  |  | Phase 2
M | Code App | 2019-08-14 | 2019-11-22 | 100 | 44 | 44 | 144 | 144 | 0 | 0 |  | Critical Path | Phase 3
N | Validate Ability to Track KPIs | 2019-11-22 | 2019-11-28 | 6 | 144 | 176 | 150 | 182 | 165 | 165 |  |  | Phase 4
O | Connect DB to App | 2019-11-22 | 2019-11-28 | 6 | 144 | 144 | 150 | 150 | 0 | 0 |  | Critical Path | Phase 4
P | Import model into App | 2019-11-22 | 2019-11-28 | 6 | 144 | 156 | 150 | 162 | 12 | 0 |  |  | Phase 4
Q | Test App | 2019-11-22 | 2019-12-04 | 12 | 144 | 162 | 156 | 174 | 18 | 18 |  |  | Phase 4
R | Test Security | 2019-11-28 | 2019-12-22 | 24 | 150 | 150 | 174 | 174 | 0 | 0 |  | Critical Path | Phase 4
S | Test Predictions | 2019-11-28 | 2019-12-10 | 12 | 150 | 162 | 162 | 174 | 12 | 12 |  |  | Phase 4
T | Launch Campaign | 2019-12-22 | 2020-01-01 | 10 | 174 | 174 | 184 | 184 | 0 | 0 |  | Critical Path | Phase 5
U | App Goes Live | 2020-01-01 | 2020-01-02 | 1 | 184 | 184 | 185 | 185 | 0 | 0 |  | Critical Path | Phase 5
V | Track KPIs | 2020-01-02 | 2020-01-05 | 3 | 185 | 185 | 188 | 188 | 0 | 0 |  | Critical Path | Phase 5
W | Build Reports | 2020-01-05 | 2020-01-20 | 15 | 188 | 188 | 203 | 203 | 0 | 0 |  | Critical Path | Phase 5
X | Evaluate Results | 2020-01-20 | 2020-01-26 | 6 | 203 | 203 | 209 | 209 | 0 | 0 |  | Critical Path | Phase 5
Formulas:
DUE DATE = C6+[EF]
START DATE = C6+[ES]

## Gantt Details
ACTIVITY ID | TASK NAME | START DATE | DUE DATE | DURATION | ES | LS | EF | LF | TOTAL SLACK | FREE SLACK | TOTAL PV | Path | SPRINT/MILESTONE
AA | Project Charter | 2019-07-01 | 2019-07-06 | 5 | 0 | 0 | 5 | 5 | 0 | 0 |  | Critical Path | Phase 1
A | Create Data Tables | 2019-07-06 | 2019-07-11 | 5 | 5 | 93 | 10 | 98 | 88 | 0 |  |  | Phase 1
B | Convert Algorithm to Python | 2019-07-06 | 2019-07-09 | 3 | 5 | 122 | 8 | 125 | 117 | 0 |  |  | Phase 1
C | Wire Frame App | 2019-07-06 | 2019-07-21 | 15 | 5 | 5 | 20 | 20 | 0 | 0 |  | Critical Path | Phase 1
D | Create Marketing Plan | 2019-07-06 | 2019-08-05 | 30 | 5 | 144 | 35 | 174 | 139 | 139 |  |  | Phase 1
E | Define KPIs | 2019-07-06 | 2019-07-15 | 9 | 5 | 170 | 14 | 179 | 165 | 0 |  |  | Phase 1
F | Compile List of Websites | 2019-07-11 | 2019-07-16 | 5 | 10 | 98 | 15 | 103 | 88 | 0 |  |  | Phase 2
G | Backtest Model | 2019-07-09 | 2019-07-23 | 14 | 8 | 125 | 22 | 139 | 117 | 0 |  |  | Phase 2
H | Design Pages | 2019-07-21 | 2019-08-14 | 24 | 20 | 20 | 44 | 44 | 0 | 0 |  | Critical Path | Phase 2
I | Write Scraping Code | 2019-07-16 | 2019-08-20 | 35 | 15 | 103 | 50 | 138 | 88 | 0 |  |  | Phase 2
J | Validate Pyton Model | 2019-07-23 | 2019-08-06 | 14 | 22 | 139 | 36 | 153 | 117 | 0 |  |  | Phase 2
K | Automate Data Pipeline | 2019-08-20 | 2019-08-26 | 6 | 50 | 138 | 56 | 144 | 88 | 88 |  |  | Phase 2
L | Export Model | 2019-08-06 | 2019-08-09 | 3 | 36 | 153 | 39 | 156 | 117 | 105 |  |  | Phase 2
M | Code App | 2019-08-14 | 2019-11-22 | 100 | 44 | 44 | 144 | 144 | 0 | 0 |  | Critical Path | Phase 3
N | Validate Ability to Track KPIs | 2019-11-22 | 2019-11-28 | 6 | 144 | 176 | 150 | 182 | 165 | 165 |  |  | Phase 4
O | Connect DB to App | 2019-11-22 | 2019-11-28 | 6 | 144 | 144 | 150 | 150 | 0 | 0 |  | Critical Path | Phase 4
P | Import model into App | 2019-11-22 | 2019-11-28 | 6 | 144 | 156 | 150 | 162 | 12 | 0 |  |  | Phase 4
Q | Test App | 2019-11-22 | 2019-12-04 | 12 | 144 | 162 | 156 | 174 | 18 | 18 |  |  | Phase 4
R | Test Security | 2019-11-28 | 2019-12-22 | 24 | 150 | 150 | 174 | 174 | 0 | 0 |  | Critical Path | Phase 4
S | Test Predictions | 2019-11-28 | 2019-12-10 | 12 | 150 | 162 | 162 | 174 | 12 | 12 |  |  | Phase 4
T | Launch Campaign | 2019-12-22 | 2020-01-01 | 10 | 174 | 174 | 184 | 184 | 0 | 0 |  | Critical Path | Phase 5
U | App Goes Live | 2020-01-01 | 2020-01-02 | 1 | 184 | 184 | 185 | 185 | 0 | 0 |  | Critical Path | Phase 5
V | Track KPIs | 2020-01-02 | 2020-01-05 | 3 | 185 | 185 | 188 | 188 | 0 | 0 |  | Critical Path | Phase 5
W | Build Reports | 2020-01-05 | 2020-01-20 | 15 | 188 | 188 | 203 | 203 | 0 | 0 |  | Critical Path | Phase 5
X | Evaluate Results | 2020-01-20 | 2020-01-26 | 6 | 203 | 203 | 209 | 209 | 0 | 0 |  | Critical Path | Phase 5
Formulas:
DUE DATE = D7+[EF]
START DATE = D7+[ES]

## Time Phase Budget
ACTIVITY ID | DURATION | TASK NAME | BUDGET (PV) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42
AA | 5 | Project Charter | 1000 | Week 1: 1000
A | 5 | Create Data Tables | 4000 | Week 2: 4000
B | 3 | Convert Algorithm to Python | 5000 | Week 2: 5000
C | 15 | Wire Frame App | 7000 | Week 2: 2333; Week 3: 2333; Week 4: 2334
D | 30 | Create Marketing Plan | 11250 | Week 2: 1875; Week 3: 1875; Week 4: 1875; Week 5: 1875; Week 6: 1875; Week 7: 1875
E | 9 | Define KPIs | 4000 | Week 2: 2000; Week 3: 2000
F | 5 | Compile List of Websites | 4500 | Week 3: 4500
G | 14 | Backtest Model | 13500 | Week 3: 4500; Week 4: 4500; Week 5: 4500
H | 24 | Design Pages | 13500 | Week 5: 2700; Week 6: 2700; Week 7: 2700; Week 8: 2700; Week 9: 2700
I | 35 | Write Scraping Code | 35500 | Week 4: 5071.4286; Week 5: 5071.4286; Week 6: 5071.4286; Week 7: 5071.4286; Week 8: 5071.4286; Week 9: 5071.4286; Week 10: 5071.4286
J | 14 | Validate Pyton Model | 13500 | Week 5: 4500; Week 6: 4500; Week 7: 4500
K | 6 | Automate Data Pipeline | 5500 | Week 11: 5500
L | 3 | Export Model | 2500 | Week 8: 2500
M | 100 | Code App | 66000 | Week 10: 3300; Week 11: 3300; Week 12: 3300; Week 13: 3300; Week 14: 3300; Week 15: 3300; Week 16: 3300; Week 17: 3300; Week 18: 3300; Week 19: 3300; Week 20: 3300; Week 21: 3300; Week 22: 3300; Week 23: 3300; Week 24: 3300; Week 25: 3300; Week 26: 3300; Week 27: 3300; Week 28: 3300; Week 29: 3300
N | 6 | Validate Ability to Track KPIs | 2750 | Week 30: 2750
O | 6 | Connect DB to App | 2750 | Week 30: 2750
P | 6 | Import model into App | 3500 | Week 30: 3500
Q | 12 | Test App | 6750 | Week 30: 2250; Week 31: 2250; Week 32: 2250
R | 24 | Test Security | 13250 | Week 31: 2650; Week 32: 2650; Week 33: 2650; Week 34: 2650; Week 35: 2650
S | 12 | Test Predictions | 9000 | Week 31: 3000; Week 32: 3000; Week 33: 3000
T | 10 | Launch Campaign | 5750 | Week 36: 2875; Week 37: 2875
U | 1 | App Goes Live | 1000 | Week 38: 1000
V | 3 | Track KPIs | 1500 | Week 38: 1500
W | 15 | Build Reports | 16000 | Week 39: 5333.3333; Week 40: 5333.3333; Week 41: 5333.3333
X | 6 | Evaluate Results | 5000 | Week 42: 5000
Week Total |  |  | 254000 | 1000 | 15208 | 15208 | 13780.4286 | 18646.4286 | 14146.4286 | 14146.4286 | 10271.4286 | 7771.4286 | 8371.4286 | 8800 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 11250 | 7900 | 7900 | 5650 | 2650 | 2650 | 2875 | 2875 | 2500 | 5333.3333 | 5333.3333 | 5333.3333 | 5000
Cummulative PV |  |  |  | 1000 | 16208 | 31416 | 45196.4286 | 63842.8571 | 77989.2857 | 92135.7143 | 102407.1429 | 110178.5714 | 118550 | 127350 | 130650 | 133950 | 137250 | 140550 | 143850 | 147150 | 150450 | 153750 | 157050 | 160350 | 163650 | 166950 | 170250 | 173550 | 176850 | 180150 | 183450 | 186750 | 198000 | 205900 | 213800 | 219450 | 222100 | 224750 | 227625 | 230500 | 233000 | 238333.3333 | 243666.6667 | 249000 | 254000

## Crash Gnatt
iPhone Application Project
A.I. Sports
Jason Lee
ACTIVITY ID | TASK NAME | START DATE | DUE DATE | DURATION | ES | LS | EF | LF | TOTAL SLACK | FREE SLACK | TOTAL PV | PRIORITY | SPRINT/MILESTONE
AA | Project Charter | 2019-07-01 | 2019-07-06 | 5 | 0 | 0 | 5 | 5 | 0 | 0 |  | Critical Path | Phase 1
A | Create Data Tables | 2019-07-06 | 2019-07-11 | 5 | 5 | 93 | 10 | 98 | 88 | 0 |  |  | Phase 1
B | Convert Algorithm to Python | 2019-07-06 | 2019-07-09 | 3 | 5 | 122 | 8 | 125 | 117 | 0 |  |  | Phase 1
C | Wire Frame App | 2019-07-06 | 2019-07-16 | 10 | 5 | 5 | 15 | 15 | 0 | 0 |  | Critical Path | Phase 1
D | Create Marketing Plan | 2019-07-06 | 2019-08-05 | 30 | 5 | 144 | 35 | 174 | 139 | 139 |  |  | Phase 1
E | Define KPIs | 2019-07-06 | 2019-07-15 | 9 | 5 | 170 | 14 | 179 | 165 | 0 |  |  | Phase 1
F | Compile List of Websites | 2019-07-11 | 2019-07-16 | 5 | 10 | 98 | 15 | 103 | 88 | 0 |  |  | Phase 2
G | Backtest Model | 2019-07-09 | 2019-07-23 | 14 | 8 | 125 | 22 | 139 | 117 | 0 |  |  | Phase 2
H | Design Pages | 2019-07-16 | 2019-07-30 | 14 | 15 | 20 | 29 | 34 | 0 | 0 |  | Critical Path | Phase 2
I | Write Scraping Code | 2019-07-16 | 2019-08-20 | 35 | 15 | 103 | 50 | 138 | 88 | 0 |  |  | Phase 2
J | Validate Pyton Model | 2019-07-23 | 2019-08-06 | 14 | 22 | 139 | 36 | 153 | 117 | 0 |  |  | Phase 2
K | Automate Data Pipeline | 2019-08-20 | 2019-08-26 | 6 | 50 | 138 | 56 | 144 | 88 | 88 |  |  | Phase 2
L | Export Model | 2019-08-06 | 2019-08-09 | 3 | 36 | 153 | 39 | 156 | 117 | 105 |  |  | Phase 2
M | Code App | 2019-07-30 | 2019-09-28 | 60 | 29 | 44 | 89 | 104 | 0 | 0 |  | Critical Path | Phase 3
N | Validate Ability to Track KPIs | 2019-09-28 | 2019-10-04 | 6 | 89 | 176 | 95 | 182 | 165 | 165 |  |  | Phase 4
O | Connect DB to App | 2019-09-28 | 2019-10-04 | 6 | 89 | 144 | 95 | 150 | 0 | 0 |  | Critical Path | Phase 4
P | Import model into App | 2019-09-28 | 2019-10-04 | 6 | 89 | 156 | 95 | 162 | 12 | 0 |  |  | Phase 4
Q | Test App | 2019-09-28 | 2019-10-10 | 12 | 89 | 162 | 101 | 174 | 18 | 18 |  |  | Phase 4
R | Test Security | 2019-10-04 | 2019-10-28 | 24 | 95 | 150 | 119 | 174 | 0 | 0 |  | Critical Path | Phase 4
S | Test Predictions | 2019-10-04 | 2019-10-16 | 12 | 95 | 162 | 107 | 174 | 12 | 12 |  |  | Phase 4
T | Launch Campaign | 2019-10-28 | 2019-11-07 | 10 | 119 | 174 | 129 | 184 | 0 | 0 |  | Critical Path | Phase 5
U | App Goes Live | 2019-11-07 | 2019-11-08 | 1 | 129 | 184 | 130 | 185 | 0 | 0 |  | Critical Path | Phase 5
V | Track KPIs | 2019-11-08 | 2019-11-11 | 3 | 130 | 185 | 133 | 188 | 0 | 0 |  | Critical Path | Phase 5
W | Build Reports | 2019-11-11 | 2019-11-26 | 15 | 133 | 188 | 148 | 203 | 0 | 0 |  | Critical Path | Phase 5
X | Evaluate Results | 2019-11-26 | 2019-12-02 | 6 | 148 | 203 | 154 | 209 | 0 | 0 |  | Critical Path | Phase 5
Formulas:
DUE DATE = C6+[EF]
START DATE = C6+[ES]

## Crash Time Phase Budget
ACTIVITY ID | DURATION | TASK NAME | BUDGET | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31
AA | 5 | Project Charter | 1000 | 1000
A | 5 | Create Data Tables | 4000 |  | 4000
B | 3 | Convert Algorithm to Python | 5000 |  | 5000
C | 10 | Wire Frame App | 9333 |  | 4666 | 4667
D | 30 | Create Marketing Plan | 11250 |  | 1875 | 1875 | 1875 | 1875 | 1875 | 1875
E | 9 | Define KPIs | 4000 |  | 2000 | 2000
F | 5 | Compile List of Websites | 4500 |  |  | 4500
G | 14 | Backtest Model | 13500 |  |  | 4500 | 4500 | 4500
H | 14 | Design Pages | 16200 |  |  |  | 5400 | 5400 | 5400
I | 35 | Write Scraping Code | 35500 |  |  |  | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286
J | 14 | Validate Pyton Model | 13500 |  |  |  |  | 4500 | 4500 | 4500
K | 6 | Automate Data Pipeline | 5500 | [10 empty] | 5500
L | 3 | Export Model | 2500 | [7 empty] | 2500
M | 60 | Code App | 79200 | [6 empty] | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600
N | 6 | Validate Ability to Track KPIs | 2750 | [18 empty] | 2750
O | 6 | Connect DB to App | 2750 | [18 empty] | 2750
P | 6 | Import model into App | 3500 | [18 empty] | 3500
Q | 12 | Test App | 6750 | [18 empty] | 2250 | 2250 | 2250
R | 24 | Test Security | 13250 | [19 empty] | 2650 | 2650 | 2650 | 2650 | 2650
S | 12 | Test Predictions | 9000 | [19 empty] | 3000 | 3000 | 3000
T | 10 | Launch Campaign | 5750 | [24 empty] | 2875 | 2875
U | 1 | App Goes Live | 1000 | [26 empty] | 1000
V | 3 | Track KPIs | 1500 | [26 empty] | 1500
W | 15 | Build Reports | 16000 | [27 empty] | 5333.3333 | 5333.3333 | 5333.3333
X | 6 | Evaluate Results | 5000 | [30 empty] | 5000
Week Total |  |  | 272233 | 1000 | 17541 | 17542 | 16846.4286 | 21346.4286 | 16846.4286 | 18046.4286 | 14171.4286 | 11671.4286 | 11671.4286 | 12100 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 11250 | 7900 | 7900 | 5650 | 2650 | 2650 | 2875 | 2875 | 2500 | 5333.3333 | 5333.3333 | 5333.3333 | 5000
Cummulative |  |  |  | 1000 | 18541 | 36083 | 52929.4286 | 74275.8571 | 91122.2857 | 109168.7143 | 123340.1429 | 135011.5714 | 146683 | 158783 | 165383 | 171983 | 178583 | 185183 | 191783 | 198383 | 204983 | 216233 | 224133 | 232033 | 237683 | 240333 | 242983 | 245858 | 248733 | 251233 | 256566.3333 | 261899.6667 | 267233 | 272233
[7 empty] | 2700 | 2700 | 2700 | 2700 | 2700
[7 empty] | 5400 | 5400 | 5400
days of work
|  |  | 7000 | 2333.3333 | 4666 | [8 empty] | 66000 | 100
[15 empty] | pay a day | pay a week
[15 empty] | 660 | 3300 | 66000
[16 empty] | 6600 | 79200
[16 empty] | 9900 | 79200

## EVA
ACTIVITY ID | DURATION | TASK NAME | BUDGET (PV) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42
AA | 5 | Project Charter | 1000 | Week 1: 1000
A | 5 | Create Data Tables | 4000 | Week 2: 4000
B | 3 | Convert Algorithm to Python | 5000 | Week 2: 5000
C | 15 | Wire Frame App | 7000 | Week 2: 2333; Week 3: 2333; Week 4: 2334; Week 5: x
D | 30 | Create Marketing Plan | 11250 | Week 2: 1875; Week 3: 1875; Week 4: 1875; Week 5: 1875; Week 6: 1875; Week 7: 1875
E | 9 | Define KPIs | 4000 | Week 2: 2000; Week 3: 2000
F | 5 | Compile List of Websites | 4500 | Week 3: 4500
G | 14 | Backtest Model | 13500 | Week 3: 4500; Week 4: 4500; Week 5: 4500; Week 6: x; Week 7: x
H | 24 | Design Pages | 13500 | Week 5: x; Week 6: 2700; Week 7: 2700; Week 8: 2700; Week 9: 2700; Week 10: 2700; Week 11: 2700
I | 35 | Write Scraping Code | 35500 | Week 4: 5071.4286; Week 5: 5071.4286; Week 6: 5071.4286; Week 7: 5071.4286; Week 8: 5071.4286; Week 9: 5071.4286; Week 10: 5071.4286
J | 14 | Validate Pyton Model | 13500 | Week 5: 4500; Week 6: 4500; Week 7: 4500
K | 6 | Automate Data Pipeline | 5500 | Week 11: 5500
L | 3 | Export Model | 2500 | Week 8: 2500
M | 100 | Code App | 66000 | Week 10: 3300; Week 11: 3300; Week 12: 3300; Week 13: 3300; Week 14: 3300; Week 15: 3300; Week 16: 3300; Week 17: 3300; Week 18: 3300; Week 19: 3300; Week 20: 3300; Week 21: 3300; Week 22: 3300; Week 23: 3300; Week 24: 3300; Week 25: 3300; Week 26: 3300; Week 27: 3300; Week 28: 3300; Week 29: 3300
N | 6 | Validate Ability to Track KPIs | 2750 | Week 30: 2750
O | 6 | Connect DB to App | 2750 | Week 30: 2750
P | 6 | Import model into App | 3500 | Week 30: 3500
Q | 12 | Test App | 6750 | Week 30: 2250; Week 31: 2250; Week 32: 2250
R | 24 | Test Security | 13250 | Week 31: 2650; Week 32: 2650; Week 33: 2650; Week 34: 2650; Week 35: 2650
S | 12 | Test Predictions | 9000 | Week 31: 3000; Week 32: 3000; Week 33: 3000
T | 10 | Launch Campaign | 5750 | Week 36: 2875; Week 37: 2875
U | 1 | App Goes Live | 1000 | Week 38: 1000
V | 3 | Track KPIs | 1500 | Week 38: 1500
W | 15 | Build Reports | 16000 | Week 39: 5333.3333; Week 40: 5333.3333; Week 41: 5333.3333
X | 6 | Evaluate Results | 5000 | Week 42: 5000
Week Total |  |  | 254000 | 1000 | 15208 | 15208 | 13780.4286 | 15946.4286 | 14146.4286 | 14146.4286 | 10271.4286 | 7771.4286 | 11071.4286 | 11500 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 11250 | 7900 | 7900 | 5650 | 2650 | 2650 | 2875 | 2875 | 2500 | 5333.3333 | 5333.3333 | 5333.3333 | 5000
Cummulative PV |  |  |  | 1000 | 16208 | 31416 | 45196.4286 | 61142.8571 | 75289.2857 | 89435.7143 | 99707.1429 | 107478.5714 | 118550 | 130050 | 133350 | 136650 | 139950 | 143250 | 146550 | 149850 | 153150 | 156450 | 159750 | 163050 | 166350 | 169650 | 172950 | 176250 | 179550 | 182850 | 186150 | 189450 | 200700 | 208600 | 216500 | 222150 | 224800 | 227450 | 230325 | 233200 | 235700 | 241033.3333 | 246366.6667 | 251700 | 256700
End of Period 1
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | 0% | 0 | 0 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: EV = Comp% x PV
B | 0% | 0 | 0 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: CV = EV - AC
C | 0% | 0 | 0 | Week 1: 7000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: SV = EV - PV
D | 0% | 0 | 0 | Week 1: 11250; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: CPI = EV / AC
E | 0% | 0 | 0 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: SPI = EV / PV
F | 0% | 0 | 0 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
G | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 2
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 7: By end of period 2 we are alreadya little behind schedule on task C (Wire Frame App) this is along the critical path
C | 33% | 2310 | 2500 | Week 1: 7000; Week 2: -190; Week 3: -4690; Week 4: 0.924; Week 5: 1
D | 16% | 1800 | 1800 | Week 1: 11250; Week 2: 0; Week 3: -9450; Week 4: 1; Week 5: 1
E | 50% | 2000 | 2000 | Week 1: 4000; Week 2: 0; Week 3: -2000; Week 4: 1; Week 5: 1; Week 8: 4666; Week 9: 9332
F | 0% | 0 | 0 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 8: work remaining
G | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 8: CPI
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 7000
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 2310
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 7: 2500
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 3
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | 50% | 3500 | 4666 | Week 1: 7000; Week 2: -1166; Week 3: -3500; Week 4: 0.75011; Week 5: 0.5
D | 33% | 3712.5 | 3750 | Week 1: 11250; Week 2: -37.5; Week 3: -7537.5; Week 4: 0.99; Week 5: 0.33; Week 7: Task C is behind pace
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 8: 2333.3333; Week 9: 9333.3333
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 33% | 4455 | 4500 | Week 1: 13500; Week 2: -45; Week 3: -9045; Week 4: 0.99; Week 5: 0.33
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 4
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | 75% | 5250 | 7000 | Week 1: 7000; Week 2: -1750; Week 3: -1750; Week 4: 0.75; Week 5: 0.75; Week 7: We can't start task H until C is complete… But that was delayed so now this project start is pushed back a week
D | 50% | 5625 | 5625 | Week 1: 11250; Week 2: 0; Week 3: -5625; Week 4: 1; Week 5: 0.5; Week 7: Task G is more difficult than anticipated and is running behind pace
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 40% | 5400 | 9000 | Week 1: 13500; Week 2: -3600; Week 3: -8100; Week 4: 0.6; Week 5: 0.4; Week 7: 22500
H | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
I | 15% | 5325 | 5071 | Week 1: 35500; Week 2: 254; Week 3: -30175; Week 4: 1.0501; Week 5: 0.15
J | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 5
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | Finished | 7000 | 9333 | Week 1: 7000; Week 2: -2333; Week 3: 0; Week 4: 0.75003; Week 5: 1
D | 66% | 7425 | 7500 | Week 1: 11250; Week 2: -75; Week 3: -3825; Week 4: 0.99; Week 5: 0.66; Week 7: Task G is behind pace. It's not along the critical path and will not cause delays to the overall project
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1; Week 7: We had a little jump start on Task H to try and make up some ground we lost.
G | 60% | 8100 | 13500 | Week 1: 13500; Week 2: -5400; Week 3: -5400; Week 4: 0.6; Week 5: 0.6; Week 7: 22500
H | 10% | 1350 | 1000 | Week 1: 13500; Week 2: 350; Week 3: -12150; Week 4: 1.35; Week 5: 0.1
I | 30% | 10650 | 10143 | Week 1: 35500; Week 2: 507; Week 3: -24850; Week 4: 1.05; Week 5: 0.3
J | 33% | 4455 | 4500 | Week 1: 13500; Week 2: -45; Week 3: -9045; Week 4: 0.99; Week 5: 0.33
K | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 35500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 13500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
End of Period 6
Task | Actual % Complete | Earned Value (EV) | Actual Cost (AC) | Week 1: PlannedValue (PV); Week 2: Cost Variance (CV); Week 3: Schedule Variance (SV); Week 4: CPI; Week 5: SPI
AA | Finished | 1000 | 1000 | Week 1: 1000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
A | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
B | Finished | 5000 | 5000 | Week 1: 5000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
C | Finished | 7000 | 9333 | Week 1: 7000; Week 2: -2333; Week 3: 0; Week 4: 0.75003; Week 5: 1
D | 84% | 9450 | 9375 | Week 1: 11250; Week 2: 75; Week 3: -1800; Week 4: 1.008; Week 5: 0.84; Week 7: Task G is killing us
E | Finished | 4000 | 4000 | Week 1: 4000; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
F | Finished | 4500 | 4500 | Week 1: 4500; Week 2: 0; Week 3: 0; Week 4: 1; Week 5: 1
G | 80% | 10800 | 18000 | Week 1: 13500; Week 2: -7200; Week 3: -2700; Week 4: 0.6; Week 5: 0.8
H | 30% | 4050 | 3700 | Week 1: 13500; Week 2: 350; Week 3: -9450; Week 4: 1.0946; Week 5: 0.3
I | 43% | 15265 | 15214 | Week 1: 35500; Week 2: 51; Week 3: -20235; Week 4: 1.0034; Week 5: 0.43
J | 66% | 8910 | 9000 | Week 1: 13500; Week 2: -90; Week 3: -4590; Week 4: 0.99; Week 5: 0.66
K | 0% | 0 | 0 | Week 1: 5500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
L | 0% | 0 | 0 | Week 1: 2500; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0
M | 0% | 0 | 0 | Week 1: 66000; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0

## Modified Cost Budget
ACTIVITY ID | DURATION | TASK NAME | BUDGET (PV) | Change | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44
AA | 5 | Project Charter | 1000 |  | 1000
A | 5 | Create Data Tables | 4000 |  |  | 4000
B | 3 | Convert Algorithm to Python | 5000 |  |  | 5000
C | 15 | Wire Frame App | 9333 | $2,333 + |  | 2333 | 2333 | 2334 | 2333
D | 30 | Create Marketing Plan | 11250 |  |  | 1875 | 1875 | 1875 | 1875 | 1875 | 1875
E | 9 | Define KPIs | 4000 |  |  | 2000 | 2000
F | 5 | Compile List of Websites | 4500 |  |  |  | 4500
G | 14 | Backtest Model | 22500 | $9,000 + |  |  | 4500 | 4500 | 4500 | 4500 | 4500
H | 24 | Design Pages | 16200 | $2,700 + |  |  |  |  | x | 2700 | 2700 | 2700 | 2700 | 2700 | 2700
I | 35 | Write Scraping Code | 35500 |  |  |  |  | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286 | 5071.4286
J | 14 | Validate Pyton Model | 13500 | [5 empty] | 4500 | 4500 | 4500
K | 6 | Automate Data Pipeline | 5500 | [11 empty] | 5500
L | 3 | Export Model | 2500 | [8 empty] | 2500
M | 100 | Code App | 66000 | [10 empty] | x | x | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300
N | 6 | Validate Ability to Track KPIs | 2750 | [32 empty] | 2750
O | 6 | Connect DB to App | 2750 | [32 empty] | 2750
P | 6 | Import model into App | 3500 | [32 empty] | 3500
Q | 12 | Test App | 6750 | [32 empty] | 2250 | 2250 | 2250
R | 24 | Test Security | 13250 | [33 empty] | 2650 | 2650 | 2650 | 2650 | 2650
S | 12 | Test Predictions | 9000 | [33 empty] | 3000 | 3000 | 3000
T | 10 | Launch Campaign | 5750 | [38 empty] | 2875 | 2875
U | 1 | App Goes Live | 1000 | [40 empty] | 1000
V | 3 | Track KPIs | 1500 | [40 empty] | 1500
W | 15 | Build Reports | 16000 | [41 empty] | 5333.3333 | 5333.3333 | 5333.3333
X | 6 | Evaluate Results | 5000 | [44 empty] | 5000
Week Total |  |  | 268033 | 14033 | 1000 | 15208 | 15208 | 13780.4286 | 18279.4286 | 18646.4286 | 18646.4286 | 10271.4286 | 7771.4286 | 7771.4286 | 8200 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 3300 | 11250 | 7900 | 7900 | 5650 | 2650 | 2650 | 2875 | 2875 | 2500 | 5333.3333 | 5333.3333 | 5333.3333 | 5000
Cummulative PV |  |  |  |  | 1000 | 16208 | 31416 | 45196.4286 | 63475.8571 | 82122.2857 | 100768.7143 | 111040.1429 | 118811.5714 | 126583 | 134783 | 138083 | 141383 | 144683 | 147983 | 151283 | 154583 | 157883 | 161183 | 164483 | 167783 | 171083 | 174383 | 177683 | 180983 | 184283 | 187583 | 190883 | 194183 | 197483 | 200783 | 212033 | 219933 | 227833 | 233483 | 236133 | 238783 | 241658 | 244533 | 247033 | 252366.3333 | 257699.6667 | 263033 | 268033