## iPhone Application Cost
Time-Cost Labor Estimates
WBS ID | Task Description | Estimate (hrs) | Estimating Approach | Estimated Duration (hrs) | Estimated Interruptions (hrs) | Total Duration (hrs) | Labor Rate $/hr | Labor Cost Total $
| iPhone Application Project | 710 | [5 empty] | 239960.1295
1 | Database | 120 | Historical |  |  |  |  | 51704.947
1.1 | Data Engineering - Create Tables | 10 | Historical | 13.3 | 4.389 | 17.689 | 225 | 3980.025
1.2 | Data Science - Build Data Pipelines | 102 | Historical | 135.66 | 44.7678 | 180.4278 | 250 | 45106.95
1.2.1 | Data Science - Compile list of websites to scrape | 10 | Historical | 13.3 | 4.389 | 17.689 | 250 | 4422.25
1.2.2 | Data Science - Write scraping code | 80 | Historical | 106.4 | 35.112 | 141.512 | 250 | 35378
1.2.3 | Data Science - Automate | 12 | Historical | 15.96 | 5.2668 | 21.2268 | 250 | 5306.7
1.3 | IT - Connect database to application | 8 | Historical | 10.64 | 3.5112 | 14.1512 | 185 | 2617.972
2.0 | Data Science - Algorithms | 75 | Historical |  |  |  |  | 32017.09
2.1 | Data Science - Convert current algorithm to Python | 65 | Historical | 86.45 | 28.5285 | 114.9785 | 250 | 28744.625
2.1.1 | Data Science - Backtest model | 30 | Historical | 39.9 | 13.167 | 53.067 | 250 | 13266.75
2.1.2 | Data Science - Validate python predictions with in-house model | 30 | Wide Band | 39.9 | 13.167 | 53.067 | 250 | 13266.75
2.1.3 | Data Science - Export final model | 5 | Wide Band | 6.65 | 2.1945 | 8.8445 | 250 | 2211.125
2.2 | IT - Import algorithm into application | 10 | Wide Band | 13.3 | 4.389 | 17.689 | 185 | 3272.465
3.0 | IT - Application | 260 | Wide Band |  |  |  |  | 85084.09
3.1 | IT - Wire Frame Application | 20 | Wide Band | 26.6 | 8.778 | 35.378 | 185 | 6544.93
3.2 | IT - Design Pages | 40 | Historical | 53.2 | 17.556 | 70.756 | 185 | 13089.86
3.3 | IT - Code application | 200 | Historical | 266 | 87.78 | 353.78 | 185 | 65449.3
4.0 | IT - Quality Assurance | 80 | Historical |  |  |  |  | 28479.29
4.1 | IT - Test application | 20 | Historical | 26.6 | 8.778 | 35.378 | 185 | 6544.93
4.2 | Data Science - Test predictions | 20 | Historical | 26.6 | 8.778 | 35.378 | 250 | 8844.5
4.3 | IT - Test security | 40 | Historical | 53.2 | 17.556 | 70.756 | 185 | 13089.86
5.0 | Marketing - Marketing | 85 | Historical |  |  |  |  | 18794.5625
5.1 | Marketing - Create marketing plan | 50 | Historical | 66.5 | 21.945 | 88.445 | 125 | 11055.625
5.2 | Marketing - Launch campaign | 25 | Historical | 33.25 | 10.9725 | 44.2225 | 125 | 5527.8125
5.3 | Marketing - Evaluate Campaign | 10 | Historical | 13.3 | 4.389 | 17.689 | 125 | 2211.125
6.0 | BI - Reporting | 90 | Historical |  |  |  |  | 23880.15
6.1 | BI - Define KPIs | 15 | Historical | 19.95 | 6.5835 | 26.5335 | 150 | 3980.025
6.2 | BI - Validate ability to track KPIs | 10 | Historical | 13.3 | 4.389 | 17.689 | 150 | 2653.35
6.3 | BI - Track KPIs | 5 | Historical | 6.65 | 2.1945 | 8.8445 | 150 | 1326.675
6.4 | BI - Build Reports | 60 | Historical | 79.8 | 26.334 | 106.134 | 150 | 15920.1

## AON
Time-Cost Labor Estimates
WBS ID | Task Description | Estimate (hrs) | Estimating Approach | Estimated Duration (hrs) | Estimated Interruptions (hrs) | Total Duration (hrs) | Labor Rate $/hr | Labor Cost Total $
| iPhone Application Project | 710 | [5 empty] | 239960.1295
1 | Database | 120 | Historical |  |  |  |  | 51704.947
1.1 | Data Engineering - Create Tables | 10 | Historical | 13.3 | 4.389 | 17.689 | 225 | 3980.025 | A
1.2 | Data Science - Build Data Pipelines | 102 | Historical | 135.66 | 44.7678 | 180.4278 | 250 | 45106.95
1.2.1 | Data Science - Compile list of websites to scrape | 10 | Historical | 13.3 | 4.389 | 17.689 | 250 | 4422.25 |  | F
1.2.2 | Data Science - Write scraping code | 80 | Historical | 106.4 | 35.112 | 141.512 | 250 | 35378 |  |  | I
1.2.3 | Data Science - Automate | 12 | Historical | 15.96 | 5.2668 | 21.2268 | 250 | 5306.7 |  |  |  | K
1.3 | IT - Connect database to application | 8 | Historical | 10.64 | 3.5112 | 14.1512 | 185 | 2617.972 |  |  |  |  | O
2.0 | Data Science - Algorithms | 75 | Historical |  |  |  |  | 32017.09
2.1 | Data Science - Convert current algorithm to Python | 65 | Historical | 86.45 | 28.5285 | 114.9785 | 250 | 28744.625 | B
2.1.1 | Data Science - Backtest model | 30 | Historical | 39.9 | 13.167 | 53.067 | 250 | 13266.75 |  | G
2.1.2 | Data Science - Validate python predictions with in-house model | 30 | Wide Band | 39.9 | 13.167 | 53.067 | 250 | 13266.75 |  |  | J
2.1.3 | Data Science - Export final model | 5 | Wide Band | 6.65 | 2.1945 | 8.8445 | 250 | 2211.125 |  |  |  | L
2.2 | IT - Import algorithm into application | 10 | Wide Band | 13.3 | 4.389 | 17.689 | 185 | 3272.465 |  |  |  |  | P
3.0 | IT - Application | 260 | Wide Band |  |  |  |  | 85084.09
3.1 | IT - Wire Frame Application | 20 | Wide Band | 26.6 | 8.778 | 35.378 | 185 | 6544.93 | C
3.2 | IT - Design Pages | 40 | Historical | 53.2 | 17.556 | 70.756 | 185 | 13089.86 |  | H
3.3 | IT - Code application | 200 | Historical | 266 | 87.78 | 353.78 | 185 | 65449.3 |  |  |  | M
4.0 | IT - Quality Assurance | 80 | Historical |  |  |  |  | 28479.29
4.1 | IT - Test application | 20 | Historical | 26.6 | 8.778 | 35.378 | 185 | 6544.93 |  |  |  |  | Q
4.2 | Data Science - Test predictions | 20 | Historical | 26.6 | 8.778 | 35.378 | 250 | 8844.5 | [5 empty] | S
4.3 | IT - Test security | 40 | Historical | 53.2 | 17.556 | 70.756 | 185 | 13089.86 | [5 empty] | R
5.0 | Marketing - Marketing | 85 | Historical |  |  |  |  | 18794.5625
5.1 | Marketing - Create marketing plan | 50 | Historical | 66.5 | 21.945 | 88.445 | 125 | 11055.625 | D
5.2 | Marketing - Launch campaign | 25 | Historical | 33.25 | 10.9725 | 44.2225 | 125 | 5527.8125
5.3 | Marketing - Evaluate Campaign | 10 | Historical | 13.3 | 4.389 | 17.689 | 125 | 2211.125
6.0 | BI - Reporting | 90 | Historical |  |  |  |  | 23880.15
6.1 | BI - Define KPIs | 15 | Historical | 19.95 | 6.5835 | 26.5335 | 150 | 3980.025 | E
6.2 | BI - Validate ability to track KPIs | 10 | Historical | 13.3 | 4.389 | 17.689 | 150 | 2653.35 |  |  |  | N
6.3 | BI - Track KPIs | 5 | Historical | 6.65 | 2.1945 | 8.8445 | 150 | 1326.675
6.4 | BI - Build Reports | 60 | Historical | 79.8 | 26.334 | 106.134 | 150 | 15920.1